## Log
ID# | Decision Under Consideration | Reference Page | Decision Owner | Alternatives Considered (n/a means Not Available) | Impacted Groups | More Information Needed? | Need to Make Decision by Deadline? (List the last responsible moment this should be decided by) | Deadline Context (Why is this date important?) | Decision Status | Decision Outcome | Date Made | Communicate(d) To: | Implementation Owner | Assumptions
1 | Adapt the new payment site to match the MJB Website redesign | All Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | Color palate for incoming site will reflect changes, especially in header and footer of payment sites | 2025-07-07 | Sonant Development | Sonant | no style guide provided however sonant grabbed color and font style from current mn courts website. This is also what was sent to Heartland for the updated payment pages.
2 | Including example text to be displayed for customer with correct syntax/format | All Search Pages | Minnesota Judical Branch | Example text will be included in all following mockups (7/7/25) | Sonant Development | n/a | n/a | n/a | Closed | Do not display sample text/case information on any of the search pages. | 2025-09-22 | Sonant Development | Sonant | understood, will not implement sample data on DL search page.
3 | All following mockups to include required fields of data that reflect requirement | All Search Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | No further mockups will be sent without these reflections | 2025-07-07 | Sonant Development | Sonant
4 | Do we remove all MJB links not related to the requirements and workflows for payment action | All Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | Remove all links from header and footer, includings links under "About the Courts,"Helpful Links," and "Get Connected." Along with ancillary links regarding social media, site maps (needs updating), or disclaimers and policy (needs updating) | 2025-07-08 | Sonant Development | Sonant
5 | What is the new system name going forward | All Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | Going forward, the name of the system is "Court Payment Center Online Payment System." This change will be reflected in the header of new site. | 2025-07-09 | Sonant Development | Sonant
6 | Are we adding additional information links that are related to the requirements and workflows for payment action? | All Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | Adding links to CPC Contact Info, new Help link, FAQ Link, Updated Disclaimer Link, Updated Site Map Link, Updated HPS Privacy Policy Link, Copyright Info Link, MCRO Link | 2025-07-10 | Sonant Development | Sonant
7 | On homepage, there's a need to include messaging areas from MJB to update customer on system outages or general messaging | Search Page - Find Your Case | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | There will be placeholder sections to accommodate this messaging, and will only appear on homepage | 2025-07-11 | Sonant Development | Sonant
8 | There needs to be more clarification/help text for customer to find their case | All Search Pages | Minnesota Judical Branch | n/a | Sonant Development | We need to ask Sonant if this fee is configurable | n/a | n/a | Open/Text | Addition of "Notice: There is a $2.34 convenience fee for using this service for each transaction" will be on site under "Find Your Case" | 2025-07-12 | Sonant Development | Sonant | xml settings or variable manager variable
9 | Are we adding additional information links that are related to the requirements and workflows for payment action on case search page? | All Search Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | Adding links to “Read the Notices on the Help Page,” "Help," "How to find citation number" | 2025-07-13 | Sonant Development | Sonant
10 | Clarifying header text on case search page | Search Page - Find Your Case | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | Header chaging to "Find Your Case or Citation" | 2025-07-14 | Sonant Development | Sonant
11 | Clarifying field text on case search page | Search Page - Find Your Case | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | Changing "DL + DOB" to "Driver's License Number" | 2025-07-15 | Sonant Development | Sonant
12 | Modify response messaging after a search result yields no results | All Search Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text | For messaging returned from searches will be customized to what field the customer used to search, and only appear after a search is performed: Case Search: "No cases match your search. The case you are searching for may be unavailable or may not exist." Citation Search: "No citations match your search. The citation you are searching for may be unavailable or may not exist.exist. If you were recently issued a citation, it may not be available in the system for up to [VMDaysBeforeEntered] days after the issue date." DL Search: "No driver’s license was found to match your search. You may search by case or citation number." | 2025-07-16 | Sonant Development | Sonant | error handline will be added to site at dev. Do you want to put in anything about how long to wait such as It may take up to 7 days for your case to be updated in this system? See #32
13 | How do we account for expierence of customer finding a search result match but needing to indicate to new system they are another party/participant on case | Party Selection page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | All following mockups are final product will include a button for customer to select the case detail, where they can select themselves as a party via radio button | 2025-07-17 | Sonant Development | Sonant
14 | Updates on search detail fields to reflect requirements | Case Detail page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Closed | All following mockups are final product will remove fields "Case Title" and Judical Officer" and adhere to required fields given to Sonant | 2025-07-18 | Sonant Development | Sonant
15 | Creation of messaging for customer informing them of ramifications of paying on their case | Case Detail page | Minnesota Judical Branch | n/a | Sonant Development, MJB Legal, MJB Finance | n/a | n/a | n/a | Closed | All following mockups are final product will include messaging MJB will provide to Sonant for this occurrence | 2025-07-19 | Sonant Development, MJB Legal, MJB Finance | Sonant
16 | Creation of messaging for customer alerting them if case is payable or not | Case Detail page | Minnesota Judical Branch | n/a | Sonant Development, MJB Legal, MJB Finance | n/a | n/a | n/a | Closed | MJB does not want a message that "case isn't payable." MJB is to create messaging that will convey alternative steps to be taken for customer, then update Sonant. Ideally customer would be able to click back to results or a cancel button |  | Sonant Development, MJB Legal, MJB Finance | Sonant
17 | “Select a Party” page will only appear if there are multiple people owing on the case. | Party Selection page | Sonant | n/a | Sonant Development | n/a | n/a | n/a | Closed | Sonant confirmed that the “Select a Party” page will only appear if there are multiple people owing on the case. | 2025-08-11 | Sonant Development | Sonant
18 | There had been questions regarding a character limit on the last name field (which is also used for business name.) due to ADA compliance | All Search Pages | Minnesota Judical Branch | Sonant proposed to truncate at 50 characters (trying to cover 80% of business rules). MJB asked Sonant how the character limit would help with ADA alignment MJB is also looking at 800 character example in MCRO and finding a common threshold for businesses. | Sonant Development |  |  |  | Closed | make sure there are test cases with person and business names. | 2025-08-11 | Sonant Development |  | No longer a concern. We will show what is in the field. It is unlikely that there are very many that are near the 800 character limit.
19 | Should there be a cap/limit on results shown upon search? | Search Results page | Minnesota Judical Branch | There was a proposal to have a fixed amount of results for ease of use for user. | Sonant Development | n/a | n/a | n/a | Closed | MJB hasn’t done any additional investigation on number of cases that could be returned – should support all. Sonant agreed, we can just extend the page and allow scrolling Only cases with a balance owed will be returned BUT we’re not putting limits on if these case can’t be paid due to active warrant or other conditions that will prevent them from paying. | 2025-08-25 | Sonant Development | Sonant
20 | What prominent place can we display notices? | All Search Pages | Sonant |  | Sonant Development | Each pages has designated notification regions noted on the mockups. Need initial message for outages on initial search pages. |  |  | Open | question on one or multiple notifications. |  | Sonant Development
21 | Can we prepopulate the current amount due in the "Make a Payment" box? | Case Detail page | Sonant |  | Sonant Development |  |  |  | Open/BizRule |  |  | Sonant Development |  | initial amount displayed will be the full amount due for the payment. Customer will have to change the amount if they can/want to pay a different amount.
22 | Is there an ability for customers to search for additional cases from the "Case/Citation Info" page? | Case Detail page | Dean Goddette | If no shopping cart key in the webservice, it should not appear on the page (should not allow search for additional cases). On this page if the party has additional cases, we would show the “you have additional cases, click here to view” as in the citation with SK flow. | Sonant Development | Customer cannot search for additional items after they have started the process. If a case has a shopping cart key, they get a link to review the other cases. They will not be able to search for unrelated cases unless they cancel and start over. |  |  | Open | Link for “You have other payable citations or cases. Click to view” – this will only appear if the shopping cart/bulk search key is present. | 2025-09-08 | MJB |  | per outcome (K)
23 | Clarifying "Cancel/Search Again" button as terms used may be redundant | Case Detail page | Minnesota Judical Branch | Using search again may lead to a separate user workflow | Sonant Development | n/a | n/a | n/a | Closed | Team discussed that “cancel” might be clearer to the customer. |  | Sonant Development | Sonant
24 | Can Sonant get clarification on Connections as part of a case id. IE, would a topic ever be shown as a business or persons name, or should it be shown in a case detail section. | Case Detail page | Minnesota Judical Branch | Discussed just having the system have the ability to just accommodate the topic if it ever came up. | Sonant Development | Want to be careful about how much concern we’re putting against the case connection type Not as concerned about knowing all case connection types. |  |  | Open/BizRule |  |  | Sonant Development |  | will implement per rule and review in QA
25 | How can we clarify MJB is referring to the application using a standarized name? |  |  |  | Sonant Development | These are all synonymous and could be used: CPC Web, IWR, Web app, web payment app. |  |  | Open |  |  | Sonant Development |  | MJB decision?
26 | What "Terms and Conditions" are correct to link to the HPS footer? | All HPS Pages | Minnesota Judical Branch |  | Sonant Development | does this need to differ from the current t/c's? |  |  | Open/Text |  |  | Sonant Development
27 | There needs to be a determination on what webservice messaging. | All HPS Pages | Minnesota Judical Branch | Sonant will continue using what they have for messaging but will pull that detail out of the current webspec | Sonant Development, MJB Legal,MJB Finance |  | 2025-09-30 | There are other aspects of the language where it’s helpful to have the mockups when determining the messaging. | Open/Text | Wally shared our work in progress IWR Messaging document where we pulled the existing verbiage and revised. Sonant will use this messaging as a baseline, knowing it isn’t 100% completed. | 2025-09-08 | Sonant Development, MJB Legal,MJB Finance | Sonant | review in QA
28 | Do we need to "dead-end" customer and request to close browser? This would cleans out history. A majority would be single citation searches, and they feel that this would be the best experience. | Payment Receipt page | Minnesota Judical Branch |  | Sonant Development | In addition to print, should we have a close or end button? |  |  | Open/BizRule |  |  | Sonant Development
29 | Will a "progress bar" be visable for customers (ADA compliance HP Pages) | All HPS Pages | Minnesota Judical Branch |  | Sonant Development | MJB needs to verfiy if progress bar is ADA digitally compliant |  |  | Open/BizRule |  |  | Sonant Development |  | In the update there will only be two pages at heartland. CC entry and account information. Other pages will be on the sonant site.
30 | For citations, confirm there is a 1:1 citation:defendant payer options | Search Page - Find Your Citation | Minnesota Judical Branch |  | Sonant Development | n/a | n/a | n/a | Closed | Informed Sonant it’s technically a 1:1 citation:defendant but there could be instance where multiples owe so should be able to handle it. | 2025-09-18 | Sonant Development | Sonant
31 | Party Selection security options for selecting a different party | Party Selection page | Minnesota Judical Branch |  | Sonant Development | n/a | n/a | n/a | Closed | Agreeed that once you select a party, that’s it….you may not go back and select a different party for a different case. You have identified who you are. | 2025-09-18 | Sonant Development | Sonant
32 | For main landing page, do we change the language to reflect a clearer tone? (Please allow 7 days from the date the citation…) | All Search Pages |  | Suggested: Please note it may take up to 7 days from the date the citation was issued to be available in this system. | Sonant Development, MJB Legal,MJB Finance | This would help people don’t think they have to wait 7 days to pay. |  |  | Open/Text |  |  | MJB |  | need final decision. Easy to change as part of QA
33 | For main landing page, editing the the casing in grey box area from "If Unsure..." to "If unsure…" | All Search Pages | Rebecca Becker | n/a | Sonant Development | n/a |  |  | Open/Text |  |  | Sonant Development |  | consistent capitalizations
34 | On search result page, editing the capitials from the verbiage of section 4. | Search Results page | Rebecca Becker | n/a | Sonant Development | n/a |  |  | Closed |  |  | Sonant Development |  | consistent capitalizations
35 | On search result page, removing gramatical error from "Plus. the convenience…" to "plus the convenience…" | Search Results page | Rebecca Becker | n/a | Sonant Development |  |  |  | Closed | Not sure what this refers to. |  | Sonant Development |  | grammar
36 | On search result page, does the passage "if paying online." need to remain if customer is already viewing this online? | Search Results page |  |  | Sonant Development |  |  |  | Open/Text |  |  | Sonant Development |  | We're assuming that customer is viewing this online with an intend to pay online as well.
37 | Is MJB changing a "Payment Group Fee?" | Review Your Payment page |  |  | Sonant Development | n/a | n/a | n/a | Closed | This fee as been removed from subsequent previews |  | Sonant Development
38 | Do we include an option for a driver's license plate number to be available for customer to search | All Search Pages | Minnesota Judical Branch | Checking on data migration and legal to score fesability to include this for launch Working with above groups and Sonant to see if work can be include to help include this on next iteration Proceed without this feature | Sonant Development, MJB Integration, MJB Legal, MJB IT Security | Need to know data security bounderies and risks. Need to know the degree of added work this would be for Intergation team |  |  | Closed | Terminated request |  |  |  | request has been rescinded
39 | We'll need an edit on the amount of capitalization is being displayed on pages. | All Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text |  |  |  |  | consistent capitalizations / grammar
40 | We need an edit of our system name going forward to: Court Payment Center Online Payment System | All Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text | This has been the court payment center for a while. Does it need to change, and if so, what should it be? |  |  |  | need to change the site name to (including break where appropriate): Court Payment Center Online Payment System
41 | We'll need a text-edit of the "Convenience Fee" passage to match font, size, and style (no italics) of the text used on the rest of page | All Search Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text | will be done when site pages are created. |  |  |  | Court Payment Center
42 | We'll need an edit on the capitalization is being displayed in help text. Should read "Select One of the Following Search Options" | All Search Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text | move away from first letter always capitalized. |  |  |  | Online Payment System
43 | Do we remove "Alert" Icon (triangle with exclamation point)? | All Search Pages | Minnesota Judical Branch | We can look for other options that do not look like a system/application error icon. | Sonant Development | n/a | n/a | n/a | Open/Text | This appears to be an open question. Decision to remove the icon and not replace.
45 | What happens with the citation number, ticket date, and offense info if it's a family case on Search Result Page? | Search Results page | Amanda Bloodsaw |  | Sonant Development, MJB Integration, MJB Legal | Amanda is gathering info on what customers need for family type cases. Do we need to see the field on the search results, if no…let’s move it to the detail page. |  |  | Open |  |  | MJB
46 | On Search Result Page, change "Ticket Date" to "Citation Date" | Search Results page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text |  |  |  |  | understood, will update when pages created for website
47 | On Search Result Page, we need to see a view of a non-single party mockup | Search Results page | Minnesota Judical Branch | n/a | Sonant Development | The search result page will look the same whether there are one or multiple parties. | n/a | n/a | Closed |  |  | MJB
48 | On all following mockup, for the results, we do not want numbers labeling the results | Search Results page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text | eliminate the word No (label) update with the word number. Change No to Number in both single and multiple items
49 | We agreed as a group against any page pagination | Search Results page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/BizRule
50 | On Select A Party Page, change "Ticket Date" to "Citation Date" | Party Selection page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text
51 | Deciding on how customers would interface with "DOB" field | Search Page - Find Your Citation by DLN | Minnesota Judical Branch | Layout should be MM-DD-YYYY Would like customer to have ability to use date picker and manually enter in date. | Sonant Development | Will we need Canadian Provinces to be included as well? Yes we are including Canadian DLN. Provinces added with State codes. | n/a | n/a | Open
52 | "State Code" should be relabeled "State" and states should be shown as a list of states that are spelled out in their entirety | Search Page - Find Your Citation by DLN | Minnesota Judical Branch | n/a | Sonant Development | May need to revisit and change to state or province? Do we need to say anything about being from a country other than USA or Canada? | n/a | n/a | Open/Text | Change title of pages from "Minnesota Court Web Payment" to "Case Details" |  |  |  |  | RR
53 | Renaming page to "Case Details" | Case Detail page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text
54 | Update the "Case/Citation Information" section to match | Case Detail page | Minnesota Judical Branch | n/a | Sonant Development |  | n/a | n/a | Open/Text | Yes. The labels will be "Case" for cases and "Citation" for citations
55 | Need to change the heading on this page | Related Payable Cases page | Minnesota Judical Branch | n/a | Sonant Development | What do you want it changed to? | n/a | n/a | Open/Text |  |  | MJB
56 | There needs to be work to group by county | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text
57 | There needs to be clarification on what things need to be added to recipt | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | Will we need Canadian Provinces to be included as well? Yes we are including Canadian DLN. Provinces added with State codes. | n/a | n/a | Open |  |  | MJB
58 | Change EPSX ID to Receipt ID | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/BizRule | EPSx Payment ID, change to Transaction ID Transaction ID change to Receipt Number |  |  |  | the EpsX PaymentId: and HPS TransactionId: are listed in MNCIS as part of the payment (as a comment), but unfortunately, are not searchable in MNCIS nor displayed in MCRO. The EP### is the receipt number from MNCIS, which Sonant gets after posting the payment. Processor Transaction ID: Number could be used by MJB to find a transaction with HPS.
59 | Remove "Payment Group Fee" | Review Your Payment page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text
61 | We need to research how there was a way to indicate a payment plan | Case Detail page | Minnesota Judical Branch | n/a | Sonant Development | MJB needs to research how info is retreived from MIS to know how to display | n/a | n/a | Open |  |  | MJB
62 | Remove “Payment Group A”, leave “Payment Summary for XXX” with XXX being the court location. This will make it easier for customer to follow. | Review Your Payment page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text
63 | Keep numbers before sections, but don’t use zeros before numbers. | Review Your Payment page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open/Text
64 | We'll need the same info as on summary: · Number (spell out number, line number), case number, citation number, party name, and amount. · Remove installment number · Remove due date. | Review Your Payment page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open |  |  | MJB
65 | We want to keep a consistent experience between the “Review Your Payment” page and the first HPS page the customer sees. | All HPS Pages | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open |  |  |  |  | *If need real estate for the page, maybe get rid of citation number. * Discussed with Sonant, HPS will just be approving credit cards – Sonant will be using tokens to make payment.
66 | Change heading to "Payment Summary" | Review Your Payment page | Minnesota Judical Branch | n/a | Sonant Development | This must be referring to the Payment Summary Page, not the Payment Receipt page | n/a | n/a | Open | This is for the Payment Summary Page, ok on mocks
67 | Remove "Payment Group Summary" | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open
68 | Move "Payment Date" to the top of payment info being displayed | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open | make date the top line in the section
69 | We'll need to find another label name for "EPSXX" | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open | Change to Transaction Number see 58
70 | We'll need to find another label name for "Processor Transaction ID" | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open | Change to Reciept Number see 58
71 | Removing "Convenience Fee" (keeping this under the "Amount Paid" section) | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open
72 | Removing "Payment Group Fee" | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open
73 | Removing "County" in both sections (summary in head and list) | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open | MJB Action
74 | We'll need to find a vocab for labels with subtotal, convenience fees, and grand total (we can't say fees) | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | What is allowed for "convenience fee"? | n/a | n/a | Open
75 | We need customers to view the same info in the listing of case as on previous "Payment Summary" page *Number (spell out number, line number), case number, citation number, party name, and amount. | Payment Receipt page | Minnesota Judical Branch | n/a | Sonant Development | n/a | n/a | n/a | Open | Change No to Number in both single and multiple items
76 | Will we need Canadian Provinces to be included as well? | Search Page - Find Your Citation by DLN | Minnesota Judical Branch |  | Sonant Development | Yes, we can include the Canadian Provinces. The list will be the states and provinces spelled out. |  |  | Open
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
Note on K9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The service fee is configurable but it’s also contractual
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This seems very broad. There are notification fields reserved on each page. Is there a specific question about a specific page?
Note on G51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add this as an separate item

## Demo To-Do List
Number | Description | Priority | State | Page | Reported Against | Assigned | Work Notes | MJB Notes | Sonant Dev | Dev Notes | Sonant QA | Playwright Test
1 | We need clarification on what the final URL(s) will be. | Low | MJB Input Needed | All Pages | Decision Log #6 | Andrey | MJB to direct Sonant on what URL will be. 12/16/25rr current sites for Odyssey and Payments: https://webpay.courts.state.mn.us/CourtWebPay https://webpay.courts.state.mn.us/paymentapplication suggest: https://webpay.courts.state.mn.us/MNCPC or spell out MNCourtPaymentCenter | MJB needs to determine preferred URL | No Action | MJB
2 | Demo site provided has latency issues. Latency seen also on hovering over help text. | Low | Cancelled | All Pages |  |  | MJB wants to make sure that the latency is due to site being on non-prod servers. | MCRO: https://publicaccess.courts.state.mn.us/CaseSearch | No Action
3 | Change header on upper right hand corner to read "MN Court Payment Center Online Payment System" | Medium | Closed Complete | All Pages | Decision Log #40 |  | Noted change is in red. This is to make it more consistant with bottom paragraph Updated 12/16/25rr | MMG: https://mmg.courts.state.mn.us/ | Closed |  |  | test003
4 | Change footer of page to reference "MN Court Payment Center Online Payment System" | Medium | Closed Complete | All Pages | Decision Log #40 | Sonant | Noted change is in red. This is to make it more consistant with top header 12/16/25rr Changed footer text.. What about this text "Thank you for using the Minnesota Judicial Branch electronic payment system." | MMG: https://mmc.courts.state.mn.us/ | Already implemented |  |  | test004
5 | Change "Case Number" field to "Enter Case Number" | Medium | Closed Complete | Search Page - Find Your Case |  |  | Noted change is in red. Visual example can be seen here, page 1 | Palm Beach Co :https://payitclerkpbc.mypalmbeachclerk.com/ | Closed |  |  | test005
6 | Change "Citation Number" field to "Enter Citation Number" | Medium | Closed Complete | Search Page - Find Your Case |  |  | Noted change is in red. Visual example can be seen here, page 2 | MyCourtConnection: mymncourtconnection.courts.state.mn.us | Closed |  |  | test006
7 | Change "Driver's License Number" field to "Enter Driver's License Number" | Medium | Closed Complete | Search Page - Find Your Case |  |  | Noted change is in red. Visual example can be seen here, page 3 |  | Closed |  |  | test007
8 | Change "Driver's License Number" field to "Enter Driver's License Number" | Medium | Closed Complete | All Search Pages |  |  | Visual example can be seen here, page 1 12/16/25rr On initial page load, the search results panel will not be displayed.. If API returns 0 records, search results will show with error message |  | Closed |  |  | test008
9 | Change "Find Your Case or Citation" to "Find your case or citation." | Medium | Closed Complete | All Search Pages | Decision Log #39 |  | Noted change is in red. Visual example can be seen here, page 1 |  | Closed |  |  | test009
10 | Change background color from blue to another color option | Low | Closed Complete | All Pages |  | MJB | MCRO has different colors for this functionality, also may need to confirm what's available to change due to ADA 12/16/25rr Sonant needs suggested color | MJB needs to determine preferred colors - want colors similar to MCRO. Check in with Wally on color options. Mary will check with Lynn T. on this. 2/19/26 | Court | specify color Mary will send three color schemes for eval
11 | Move MJB editable message area (our proposed message area that persists on all pages) to the bottom of screen | Medium | Closed Complete | All Pages | Decision Log #20 |  | 12/16/25rr all page message will be displayed at bottom |  | Closed
12 | Change "spyglass" icon to word "Find" for customer to initiate search. | High | Closed Complete | All Search Pages |  |  | This would match what is being used on MCRO |  | Closed |  |  | test012
13 | Edit radio buttons to have selection mark be more centered within the radio buttom | Medium | Closed Complete | All Search Pages |  |  | 12/16/25rr replaced with bootstrap radio button. |  | Closed |  |  | n/a
14 | Change "Select A Party" to "Select a Party" | Medium | Closed Complete | Party Selection page | Decision Log #39 |  | Noted change is in red. |  | Closed |  |  | test014
15 | Change text on "Search again" button to "Search Again" | Medium | Closed Complete | Party Selection page |  |  | Noted change is in red. Visual example can be seen here, page 2 |  | Closed |  |  | test015
16 | Change text on "Search again" button to "Search Again" | Medium | Closed Complete | Case Detail page |  |  | Noted change is in red. Visual example can be seen here, page 3 12/16/25rr duplicate of above |  | Closed |  |  | test016
17 | Change "CASE DETAILS" to "Case Details" | Medium | Closed Complete | Case Detail page | Decision Log #39 |  | Noted change is in red. |  | Closed |  |  | test017
18 | Provide a way to return to search results on page, rather than conduct an entirely new search. Have "Return to Case Search" on top of page to model after MCRO current state. | High | Closed Complete | All Pages |  |  | 12/16/25rr requested examples in MCRO to review |  | Closed
19 | Demo case detail result did not display "Citation Number" on page | High | Closed Complete | Case Detail page | IVR.IWR Integration Solution Requirements #11 |  | 51920250823 is example 12/16/25rr bug in code.. Now displaying cittion number. |  | Closed |  |  | test019
20 | Provide a notificiation or visual icon that gives customer a confirmation that a item is added to the cart. | High | Closed Complete | Case Detail page |  |  |  |  | Closed |  |  | test020
21 | Change "Add/View" label to "View" | High | Closed Complete | Search Results page |  |  | Noted change is in red. Visual example can be seen here, page 4 |  | Closed |  |  | test020
22 | Change "Update/View" label to "Update" | High | Closed Complete | Search Results page |  |  | Noted change is in red. Visual example can be seen here, page 4 |  | Closed |  |  | test020
23 | Change "Remove" label to "Remove from Cart" | High | Closed Complete | Search Results page |  |  | Noted change is in red. Visual example can be seen here, page 4 |  | Closed |  |  | test020
24 | Non-applicable fields should not appear as there is no data to display. | High | Closed Complete | Search Results page |  | Sonant | Visual example can be seen here, page 4 | MJB needs to correct link in column H. Adam: Replaced link, but if it still doesn't work, file is in shared Sonant/MJB SharePoint site, in documents>design> "IVR Feedback - 12.08.25" 2/3: Requirement 97 includes citation number because they may not know case number. 2/19/26 - Reg believes this requirement has been satisfied with #50 2/23/26 - MJB, this is probably resolved by other requirements 27,28; leaving open for testing. | Court | Contradicts with 97 Covered by new requirement above 50
25 | Change header on top of the page from "Related Payable Cases" to "Search Results" | High | Closed Complete | Search Results page |  |  |  |  | Closed |  |  | test025
26 | Remove "Search Results" label from results box. | High | Closed Complete | Search Results page |  |  | As the heading will say "Search Results," the label is in the box is no longer needed. |  | Closed |  |  | n/a
27 | Replace "N/A" as a field result with "-" | Medium | Closed Complete | Search Results page |  |  | Noted change is in red. DA concern 12/16/25rr I know this was on hold but it got into the update replaced 18 places where it showed N/A to "-" let us know after the DA review if it needs to change. |  | Closed
28 | Ensure charges is not displayed on all family non-criminal cases. | High | Closed Complete | Search Results page | IVR.IWR Integration Solution Requirements #12 | Sonant | 12/16/25rr Need example.. If MNCIS returns charges for family cases, then it will be displayed. The application has information about whether it's family case or not. Sonant can test with 25-FA-25-14. 1/8 - this relates to any case without charges in the schema (non-criminal cases shouldn't have H103charges). | 2/23/26 - Updated description of requirement | Already implemented |  |  | test028
29 | Verify customer can change amount they are paying on payment plan | Blocker | Closed Complete | Payment Plan Details |  | Sonant | 12/16/25rr Not known what is meant. Most of the payment plans in the system now are past due so they cannot change the amount and the full payment is due. If a plan is not in arrears they can change the amount. 12/22 Allow for any amount to be entered even if past due (per cpc meeting 12/22) | 2/9: Minimum payment configurable - this should remain. Set in variable manager. | Dev Done | If the payplan is due, then full due amount will show only for guidance.. The input will allow any amount. Same applies for scenario next due amont.. The guidance amount will not enforce the amount to enter. User can enter any amount greater that Variable Manager's MinPaymentAmount ( set to $1 ).. |  | test029
30 | Change header to "Payment Plan Details" | High | Closed Complete | Payment Plan Details |  |  | 12/16/25rr Make header dynamic.. If case in payment plan will display "Payment Plan Details", other "Case Details" |  | Closed | Check
31 | Ensure all case details sections match on each indivial case, located on one page | High | Cancelled | Payment Plan Details | IVR.IWR Integration Solution Requirements #9 | MJB Team | From Webservice Business Rules, Search Results should contain: • Case number • Citation number (when included in MIS) • Case type • Case location • Case status • Date filed • Offense information: offense count, charge description, and offense date (when included in MIS) • Citation date (when included in MIS) 12/16/25rr Payment plans don't have case information. It only has all case numbers, citation number. 1/8: Lets revisit this one. The case information should be in the schema. | MJB needs to determine payment plan fields Adam: Cancelled this requirement as this is replaced with later requirements in more detail. 1/26 | No Action | Check
32 | Dollar value field must be editable to customer to change "Make a Payment of" amount. | Blocker | Closed Complete | Payment Plan Details |  | Sonant | 12/16/25rr ?? Not sure what was meant. The text is already "Make a Payment of".. Removed ":" at end, if that was meant. | 2/9: Minimum payment configurable - this should remain. Set in variable manager. | Duplicate | Same as 29 |  | test032
33 | Item #3 in "Make Payment" disclaimer should be either all bolded or highlighted to have this stand out to customer. | Medium | Cancelled | Payment Plan Details |  |  | 12/16/25rr Need example what this means. 12/22 court is still working on IWR text document. 12/22 MAK: Canceling this item, will be covered with all IWR Messaging changes. |  | No Action | Check
34 | Review dynamic triggers that produce different user workflows to review details and make payments. | High | Cancelled | All Pages | IWR Messaging |  | 12/16/25rr Need more information or context 12/24 MAK: Canceling this item, will be covered with IWR Messaging. |  | No Action | Check
35 | Remove underline under "proof of insurance" | Low | Closed Complete | Payment Plan Details |  |  | 12/16/25rr Remove underline in fulll payment panel. |  | Closed |  |  | test035
36 | Move disclaimer of leaving site above pay and search buttons | Medium | Closed Complete | Payment Plan Details |  |  | 12/16/25rr For consistency for payment plan payment, the message "Please Note: A convenience fee of $2.34 will be added to this amount." was move above pay and search buttons. |  | Closed |  |  | test036
37 | Create button that says "Remove from Cart" to replace "X" symbol. | Medium | Work in progress | Payment Summary page |  | Sonant | 12/16/25rr Where do we place "Remove from Cart" button.. Placing it at the end, makes the totals not aligns.. Placing at start with no header makes it not properly aligned. Can we remove the functionality on this change and only allow Remove in Search Results page. 12/22, changed button to "Remove" and shift the number column to right or center justified. 3/16/26 Change "Remove" to "Remove from Cart" (DA Failure) | 2/3: See requirement 71. Sonant stated they made the change from the X to the "Remove to Cart" 3.16.26 mtg discussed the need for "Remove from Cart" verbiage to be consistant | In QA | The court agreed to shorter Remove button. Brought back "Remove from Cart" caption.
38 | Have county listing not centered on page, and have the county information align left. | Low | Closed Complete | Payment Summary page |  |  | 12/16/25rr aligned sn-header only for payment summary page to left.. |  | Closed |  |  | test038
39 | We need informational links on footer (Disclaimer, Privacy Policy, Terms of Use, Sitemap) | Low | MJB Input Needed | All Search Pages |  | Adam | MJB is discussing links with our legal dept. | 12/24 - Adam, need more detail added into this one. Adam: Completed 2/3: MJB reviewing. 2/19/26: Do we have footer links for Sonant? 2/23/26- MJB are checking if links are going to the right place, in middle of legal review. | Court | Should this be assigned to court? |  | test039
40 | We need refined text in help buttons next to search criteria. | Low | Closed Complete | All Pages |  | MJB Team | MJB is discussing text within project team. | 2/3: Added as requirement 99. | Duplicate | Satisfied by 99
41 | We need refined text in gray box area | Low | Cancelled | Party Selection page |  | MJB Team | Text currently reads, "The case you selected has multiple parties. Please choose the party related to your case. If unsure, refer to your court notice." Can reach Party Seleciton page using citation number 32820250810 | 2/3: Can we see the changes to the site before this is determined? | Duplicate | Satisfied by 99 |  | test041
42 | We need refined text that appears at the bottom of the page in brown. | Low | Closed Complete | Party Selection page |  | MJB Team | Text currently reads, "If your name is not listed or you're unsure which party to select, please return to the search page and try again." Can reach Party Selection page using citation number 32820250810 | 2/3: Remove brown text. 2/19/26: (Reg) Need refined text current: "If your name is not listed or you're unsure which party to select, please return to the search page and try again." I think this was discussed in the last meeting, but nothing ended up in our notes. 2/23/26- MJB, we asked for this to be removed. Agreed with Sonant to remove text here and case selection page. | Dev Done | What should the text be? It was discussed but doesn't seem to have been capture in the doc. Removed the brown text at bottom of page on CaseSelection and PartySelection page. |  | Cancelled
43 | We need refined text when case/citation cannot be paid |  | Cancelled | Case Detail page |  |  | MJB is discussing text within project team; text needs to not mention "court appearance." 12/24: Moving to Canceled. This will be covered with IWR document. |  | No Action
44 | We need refined text when other cases are eligible for payment. | Low | Cancelled | Case Detail page |  | MJB Team | Currently text reads, "You have other payable citations or cases. Click to view" "Click to view" is not digitally accessible. Page can be reached searching case: 25-JV-25-4 | 2/3: This should be resolved with the implementation of messaging in IWR document. | Dev Done | The "Click to view" link already has an aria-label="View other payable citations or cases" makes it compliant with WCAG 2.4.4 (Link Purpose in Context). See #1997 & #1998 TFS Bugs |  | test044
45 | Remove "NOT FOUND" subheader as result from a search yielding no results |  | Cancelled | Case Detail page |  |  | 12/24: Moving to canceled, this will be covered by IWR Messaging |  | No Action
46 | DL Search Option - Not able to use State Drop-down with keyboard | Medium | Work in progress | Search Page - Find Your Citation by DLN |  | Sonant | 12/22 enter dl in dl box and tab to state. State needs to be keyboard usable. 3.16.26 Still can't use keyboard. Is this a real-time search? | 3.16.26 mtg- Must be able to use keyboard without using arrow keys first | In QA | Drop down should work with both arrow keys and enter Entering keys while the drop-down is closed, will automatically open the dropdown and filter based on key entered. The user can select from the filtered list and press enter to make the selection.
47 | On search results, can we prevent case numbers from wrapping | Low | Closed Complete | All Search Pages |  | Sonant |  | 2/3 - Case number 27-VB-15-270215201094 is an example. First, complete a Case Number search, then select “Click to view” to see the other cases/citations. On that screen, you can see many examples of case numbers that are wrapping in the first section. It appears the Case Number field in the bottom section is much larger and not resulting in case wrapping. MNCIS max length is 23 varchar. | Dev Done | If case number is less than or equal to 15, it will fit in single line ( example 66-T3-95-0068461 ).. If it's more than 15 characters, it will wrap to two lines breaking on - character.
48 | Inconsistent messaging when searching by Case versus searching by DL number. | High | Closed Complete | Search Results page |  | Sonant | The system presents a different message when viewing the case from the search results. Case: 27-VB-17-146001 - if you initially search using this number you do get the collections message but if you search by another case, you do not get a notification that 27-VB-17-146001 was referred to collections. | 2/3: When case is searched by case number, getting referred to collections message. If look by DL number, then select the case, customer is shown different message. In theory, this should be resolved with IWR messaging but team is unsure why two different messages would be displayed by the system for the same case. | Dev Done | This one is a bug. For multiple cases, it was always checking the first case payor's flags..
49 | Search by citation/Case with a value of 1 should to go to citation results to pick a case/citation first not party selection | Blocker | Cancelled | Party Selection page |  | Sonant | Reviewed with Sonant 12/22. | 2/3: This became requirement 97. | Dev Done | Check
50 | IWR Messaging - Citation Search - No Results Found - Error message not showing days configuration | Medium | Closed Complete | Search Page - Find Your Citation | IWR Messaging | Sonant | When Search citation search doesn't return results the message reads, "No citations match your search. The citation you are searching for may be unavailable or may not exist. If you were recently issued a citation, it may not be available in the system for up to 0 days after the issue date" The zero should show the value for [VMDaysBeforeEntered] | 12/29: Reviewed with Sonant | Dev Done | Check
51 | If a search doesn't yield results and the customer changes how they're searching (ex: change from case search to citation search) - the "No Match" verbiage should disappear. | Medium | Work in progress | All Search Pages |  | Sonant | Return to default initial view. | 12/29: Reviewed with Sonant 3.16.26 Error detail persists, even when page is refreshed, discussed at 3.16.26 mtg that the message needs to be removed when switching options. | In QA | Currently, when there are no results it shows "No cases match your search" in big square below the radio button. Then when you switch search method, the text "No Cases..." disappears Expected:The error message should clear when a different type of search is selected. There was an issue with javascript, which prevented it from showing result panel on initial page load.. Now it will show the panel when the radio buttons are changed.. Also after no result search and switching to another radio button will clear no result message and show default search message.
52 | IWR General Error - Case/Citation When “cases”: > “requiresCourtContact”:true | Medium | Closed Complete | Case Detail page | IWR Messaging | Sonant | Search using Adult Criminal: 66-T3-95-006846 Change messaging to match IWR Document: Header: Unable to Make Payment This case is not able to be paid using this system. Please contact district court administration regarding this case. Make "contact district court administration" link to: https://mncourts.gov/find-courts | 12/29: Reviewed with Sonant 2/3: example case alredy provided, what more is needed? | Dev Done |  |  | test052
53 | Error - Case Not Able to be Paid | High | Closed Complete | Case Detail page | IWR Messaging | MJB Team | Search using: 40-VB-25-3. Case detail page incorrectly displayes a message of "Not Found" Messaging also displays, "Either it has already been paid or it requires a court appearance." If this is zero balance it shouldn't say anything about a court appearance. Detail page showed there were additional payable cases but when link was clikced, there was a message of "No additional cases found for this payor" appeared on the site search page (brought user away from details page to homepage). | 2/3: For the "Click to view" - Sonant stated that SK key was sent. The shopping cart key indicates if the person was eligible . Will change "You have other payable…" to "You may have other payable…" We discussed that if there are no additional cases, we wil show that message on the detail page. If there ARE other cases, the customer will be taken to a search results page with the case they searched from at the top of the search results. | Dev Done | If a case has SK key but related search doesn't return any cases, the flow will remain on Case Detail page and the "Click to View" link will disappear. Regarding, incorrect message it should be handled by other case detail message needs. |  | test053b
54 | Special Characters | Low | Closed Complete | Case Detail page |  | Sonant | Search by Citation number: 32820250810, There are special characters displaying instead of the State Satute symbols. | 12/29: Reviewed with Sonant &#167; | Dev Done | Replaced § with unicode equivalent &#167; |  | test054
55 | DL Search Option - Find Button Alignment | Low | Closed Complete | Search Page - Find Your Citation by DLN |  | Sonant | The alignment of the "Find" button will go outside the boundaries of the search box when minimized. | 12/29: Reviewed with Sonant | Dev Done | Change md layout, so the button doesn't overlay the container
56 | IWR General Error – Payment Plan \When “planCases”: > "requiresCourtContact":true | Medium | Work in progress | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment This payment plan is not able to be paid using this system. Please contact district court administration regarding this payment plan. Make "contact district court administration" link to: https://mncourts.gov/find-courts | 12/29: Reviewed with Sonant Can we provide a payment plan number? | Dev Done
57 | IWR - No Balance Due, Case Closed, Payment not allowed When "caseIsEligibleForPayment": false and "hasOutstandingBalance": false Replace “Case” with “Citation” when “charges”: “citationNumber”: has a value (not Null) | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment This {case/citation} is not able to be paid using this system because there is no amount due on this {case/citation}. | 12/29: Reviewed with Sonant Adult Criminal: 40-VB-25-3 JV Criminal: 25-JV-25-6 Non-Criminal: 70-CV-25-54 | Dev Done | for PaymentPlan checks if any paymentPlan.PlanCases.CaseIsEligibleForPayment = false for all cases.
58 | IWR Messaging - Pending {case/citation} Payment - Payment not allowed Determined by Sonant ESPX | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment A payment was recently made and it may take up to two (2) business for the payment to be processed. Payment will be credited as of the day it was made. | 12/29: Reviewed with Sonant | Dev Done | Changed for both case and payment plan pending update messaging.
59 | IWR Messaging - Active Warrant – Case/Citation When “payors”: > "hasActiveWarrant":true | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment – Active Warrant The amount due on this case cannot be paid using this system because a warrant has been issued. Contact district court administration immediately to resolve this matter. Make "contact district court administration" link to: https://mncourts.gov/find-courts | 12/29: Reviewed with Sonant Adult Criminal: 25-CR-25-13 Non-criminal: 70-CV-25-50 Single-case Payment Plan: 72-VB-25-10 Multi-case Payment Plan: 72-VB-25-11 & 72-VB-25-12 | Dev Done | Changed for case messaging
60 | IWR Message - Active Warrant – Payment Plan When “paymentplan”: > “hasActiveWarrantforPayor":true | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment – Active Warrant The amount due on this payment plan cannot be paid using this system because a warrant has been issued on one or more cases on this payment plan. Contact district court administration immediately to resolve this matter. Make "contact district court administration" link to: https://mncourts.gov/find-courts | 12/29: Reviewed with Sonant Can we provide a payment plan number? | Dev Done
61 | IWR Message - Referred to Collections – Case When “payors”: > "hasActiveReferredToCollectionsStatus": true Or "hasPaymentPlanActiveReferredToCollectionsStatus": true | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment – Referred to Collections The amount due on this case cannot be paid using this system because the amount due is past due and has been referred to the Department of Revenue (DOR) for collection action. For payment options, contact the Department of Revenue at https://www.revenue.state.mn.us/make-payment or 1-800-657-3909. | 12/29: Reviewed with Sonant | Dev Done
62 | IWR Message - Mandatory Appearance – case When “cases”: > "requiresMandatoryCourtAppearance":true | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment – Court Appearance Required The amount due on this case cannot be paid using this system because this case requires mandatory court appearance. | 12/29: Reviewed with Sonant Adult Criminal: 43-CR-25-8 JV Criminal: 25-JV-25-5 Adult Criminal w/ Endangerment: 43-CR-25-5 | Dev Done | Changed for case messaging. Previously if requiresMandatoryCourtAppearance was set, we also checked these condition 1. HasDlSuspension -> ShowContactCout 2. HasOutStandingBalance -> ShowContactCourt 3. CurrentStatus = "closed" -> ShowCaseNotFound.. All these conditions are removed and it will always show same messaging for requiresMandatoryCourtAppearance.
63 | IWR Message - Mandatory Appearance – payment plan When “planCases”: > "requiresMandatoryCourtAppearance":true | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment – Court Appearance Required The amount due on this case cannot be paid using this system because one or more of the cases on this payment plan requires a mandatory court appearance. | 12/29: Reviewed with Sonant Single-case payment plan: 43-CR-25-6 Multi-case payment plan: 43-VB-25-12 & 43-CR-25-7 | Dev Done | Changed from ShowContactCourt to ShowMandatoryAppearance panel..
64 | IWR Message - Mandatory Appearance – citation notice When “cases”: > "requiresMandatoryCourtAppearance":true OR “planCases”: > "requiresMandatoryCourtAppearance":true AND “charges”: “citationNumber”: has a value (not Null) | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment – Court Appearance Required If you received a citation, the court will send you a notice indicating when to appear. You must appear in court as required. If you did not receive notice or the court date has passed and you did not appear contact district court administration immediately to resolve this matter. Failure to appear in court may result in the suspension of your driver’s license, the issuance of a warrant for your arrest, or both. If you have questions, contact district court administration. Make both instances of "contact district court administration" link to: https://mncourts.gov/find-courts | 12/29: Reviewed with Sonant Can we provide a citation number? | Dev Done | Need example
65 | IWR Messaging - License Suspended – Criminal Case/Citation When “caseCategory”: “CR” AND “payors”: > "hasDLSuspension ": true Or “planCases”: > " hasDLSuspension":true | Medium | Testing | Search Results page | IWR Messaging | Sonant | Records show your driver’s license has been suspended. If the suspension was due to non-payment, the Department of Public Safety (DPS) will be notified when it is paid. If you have a question about the status of your driver’s license, contact the Department of Public Safety at https://dps.mn.gov/divisions/dvs or 651-297-3298. | 12/29: Reviewed with Sonant Adult Criminal: 43-VB-25-8 Non-criminal: 25-FA-25-15 Single-case Payment Plan: 43-VB-25-9 Multi-case Payment Plan: 43-VB-25-10 & 43-VB-25-11 There will not be a version of this message for non-criminal cases (license suspension only applies to CR cases). No header was provided, this message could be displayed in conjunction with other messaging. | Dev Done
66 | Party Selection Page - Displaying currentAmountDue from API schema instead of totalAmountDue when payment plans are displayed. | High | Work in progress | Party Selection page |  | Sonant | Case 04-CV-13-90: There are 3 parties on the case - 2 parties do not have a balance owed - 1 party has a $50.00 balance owed. However, their payment plan is “early”, so the currentAmountDue is 0 On the party selection page, all 3 parties are listed with $0.00 Once you select the party and continue, it does display the $50.00 amount due (with the $50 minimum issue already reported) | 12/29: Reviewed with Sonant 3.16.26 Failed testing and discussed at mtg- Still showing current amount due instead of total amount due | In QA | Always use payor's totalAmountDue to show in party selection page.
67 | Search by DL Number - MJB would like to have the State field default to MN and have the MN option appear alphabetically | Low | Closed Complete | Search Page - Find Your Citation by DLN |  | Sonant |  | 12/29: Reviewed with Sonant | Dev Done
68 | For "breadcrumb" feature, we need the ability to add a "Party Select/Search Result" option | High | Needs Discussion | All Pages |  |  | Related to #69 on to-do list | 3.16.26 mtg- discussed failed testing | In QA | Added Breadcrumb upto CaseDetail page.. If related search is initiated, breadcrumb will no longer allow user to go back to CaseSelection or PartySelection ( to change their selected case )
69 | We need to add a buttons that allow user to "Return to Search Results" on the detail pages. If user got to the detail page from party selection page, then button would read "Return to Party Selection" | High | Needs Discussion | Case Detail page |  |  | If user goes straight to details, no "Return…" button would appear. Related to #68 on to-do list | 3.16.26 mtgg-discussed failed testing | In QA | Buttons like bread crumbs are context sensitive.. They know where they come from and change the text based on that either "Return to Search Results" or "Return to Case Selection" and so on.. The only exception is DL search exception path ( when multiple parties are returned ), we can't do it..
70 | Switch the order of the buttons, where "Continue" is the first button and the last button is "Search Again" | Medium | Work in progress | Search Results page |  |  |  | 2/29/26: (Reg)Switch the order of buttons. Note, there was also a request to left align the buttons vs right alignment in 71. We have left aligned the buttons but may need clarification. We have two types of buttons.. Forward actions buttons ( in brown color ) and backward action buttons ( in gray color ).. In left aligned button pages, what types of actions should be placed on the left. The case detail page will have 3 buttons ( with #69 change ), and grouping of like actions will be better visually. Currently backward action buttons are on left and forward action buttons are on right. Is this acceptable or do we still need to switch the buttons? In the case of #69 what should the order be? 2/23/26- MJB, we still need buttons align alike on all pages. Push this to test and we'll make a determination. After conversation, Sonant will leave as is and we'll assess during testing. | Dev Done | Not sure if this will work with #71 which requies the button to be left aligned on the page.. We have two types of buttons.. Forward actions buttons ( in brown color ) and backward action buttons ( in gray color ).. In a left aligned buttons in pages, what types of actions should be placed on the left. The case detail page will have 3 buttons ( with #69 change ), and grouping of like actions will be better visually. Currently backward action buttons are on left and forward action buttons are on right. Court to make decision.
71 | For overall button placement, left align all buttons on all pages | Medium | Testing | All Pages |  |  |  |  | Dev Done | Change CaseSelection, PartySelection, SearchResults and PaymentSummary pages to align buttons to left.
72 | Ensure a uniform size on all buttons. | Low | Work in progress | All Search Pages |  |  |  | 2/29/26: (Reg)Ensure a uniform size on all buttons: Buttons across the application use varying text lengths (e.g., "Find", "View", "Remove from Cart", "Return To Search Results", "Review Payment"). Bootstrap sizes buttons to fit their content by default. On mobile, buttons already display at full width uniformly. On desktop, enforcing a single fixed width would either waste space on short labels or risk truncating/wrapping long ones. A min-width could be applied, but short buttons like "Find" would appear disproportionately wide. If uniform sizing is desired, the court would need to standardize button label lengths (e.g., abbreviate "Remove from Cart" → "Remove") so a single width works for all. 2/23/26 - MJB, we are going to amend this requirement to ensure button fit their content by default. Push this to test and we'll make determination. If something looks odd, MJB will flag during testing. | Dev Done | Buttons across the application use varying text lengths (e.g., "Find", "View", "Remove from Cart", "Return To Search Results", "Review Payment"). Bootstrap sizes buttons to fit their content by default. On mobile, buttons already display at full width uniformly. On desktop, enforcing a single fixed width would either waste space on short labels or risk truncating/wrapping long ones. A min-width could be applied, but short buttons like "Find" would appear disproportionately wide. If uniform sizing is desired, the court would need to standardize button label lengths (e.g., abbreviate "Remove from Cart" → "Remove") so a single width works for all. Court to make decision.
73 | 1. Add new indicator to “paymentPlan” data regarding financials: "alternateTotalAmountDue": a. Set to ‘false’ if financial transactions and payment plan/schedule match b. Set to ‘true’ if financial transactions and payment plan/schedule amounts don’t match i. If ‘true’ – use Tyler API GetCaseFeeBalance to get minimum financial info: 1. payment plan ID 2. remaining balance | Medium | Testing |  |  |  |  | 2/19/26: (Reg) 1. Add new indicator to “paymentPlan” data regarding financials: "alternateTotalAmountDue": a. Set to ‘false’ if financial transactions and payment plan/schedule match b. Set to ‘true’ if financial transactions and payment plan/schedule amounts don’t match i. If ‘true’ – use Tyler API GetCaseFeeBalance to get minimum financial info: 1. payment plan ID 2. remaining balance Should this be assigned to the Court? The only use case for Sonant for this field is use it on Case Detail for messaging, which is already done. Whenever the court implements the logic mentioned, it should be ready to test. 2/23/26 - Moved status to testing. | Dev Done | Should it be assigned to Court? The only use case for Sonant for this field is use it on Case Detail for messaging, which is already done.. Whenever courts implements the logic mentioned, it should be ready to test.
74 | Results are not displaying the correct party connection, all results are showing "Defendant" | Medium | Testing | Payment Plan Details | requirements 13, 16, and 19 | Sonant | Example case: 10-CV-26-1 | Example file is in shared Sonant/MJB SharePoint site, in documents>design> "EP298 - Sonant Web Design - non-criminal examples" | Dev Done | The party connection is no longer displayed on party selection page. Not applicable anymore.
75 | Case information is not being displayed as indicated in the requirements in all searches. After completing a case number search, user is brought to the Payment Plan Details page with limited data displayed. Response contains data in fields indicated in the requirements. | Medium | Testing | Payment Plan Details | Related to requirements 9, 11, 12, 13, 14, 15, 16, 17, 18, and 19 | Sonant | Example case: 10-CV-26-1 | Example file is in shared Sonant/MJB SharePoint site, in documents>design> "EP298 - Sonant Web Design - non-criminal examples" 2/23/26 - Ready for testing | Dev Done | What data needs to be displayed on case detail page for payment plan? I don't have access to documents referenced. Marked for tesing.
76 | Do not display fields when they are not applicable. Response does not include a "charges" section where this data would be retrieved from. | Medium | New | Case Detail page | Related to requirements 11 and 12 | Sonant | Example case 70-CV-25-40 | Example file is in shared Sonant/MJB SharePoint site, in documents>design> "EP298 - Sonant Web Design - non-criminal examples" | Already implemented
77 | Display fields (entered in work notes) upon search results and payment plans. MJB doesn't need result expansions. Detail pages should show all cases and details of plans. | Medium | Testing | Search Results page |  | Sonant | * Number (numbering items in results) * Case number * Case Type * Location * Amount Due (should be total amount due). * Cart amount |  | Dev Done | For cases, removed Status column. Also removed the result expansion. What columns should be displayed for payment plans.. Currently, we have Number, Case Number, Past Due, Current Due, Total Due and Cart Amount.
78 | IWR Messaging - Case Search – No Results Found When "cases": [] is returned following a case search | Medium | New | Search Results page | IWR Messaging | Sonant | Header: No cases match your search. The case you are searching for may be unavailable or may not exist. |  | Already implemented | Should be closed?
79 | IWR Messaging - Citation Search – No Results Found When "cases": [] is returned following a citation search | Medium | New | Search Results page | IWR Messaging | Sonant | Header: No citations match your search. The citation you are searching for may be unavailable or may not exist. If you were recently issued a citation, it may not be available in the system for up to [VMDaysBeforeEntered] days after the issue date. |  | Already implemented | Should be closed?
80 | IWR Messaging - Driver’s License Search – No Results Found When "cases": [] is returned following a DL search | Medium | New | Search Results page | IWR Messaging | Sonant | Header: No driver's license was found to match your search. You may search by case or citation number. |  | Already implemented | Should be closed?
81 | IWR Messaging - General Error – Case/Citation When “cases”: > “requiresCourtContact”:true | Medium | Testing | Search Results page | IWR Messaging | Sonant | Header: Unable to Make Payment This case is not able to be paid using this system. Please contact district court administration regarding this case. |  | Dev Done | Duplicate of 52
82 | IWR Messaging - Proof of Insurance When “cases” > "caseIsEligibleForPayment": true, AND When “caseCategory”: “CR” AND “baseCaseType”: “Traffic” and “charges”: “citationNumber”: has a value (not Null) and “chargeDescription” includes “insurance” | Medium | Work in progress | Search Results page | IWR Messaging | Sonant | Header: Do not pay at this time if you are charged with No Proof of Insurance or No Insurance and the vehicle you were driving was insured on the date of the offense. You may be able to have this charge dismissed by providing valid proof of insurance coverage or the name and address of the owner of the vehicle (if not yourself) to the MN Court Payment Center (CPC) no later than 30 days from when the citation is filed with the courts. Valid proof must be one (1) of the following: • Copy of the insurance coverage card for the vehicle; OR • Letter from the insurance agent; OR • Copy of the insurance policy. For more information and to submit proof of insurance go to: https://mncourts.gov/pay-a-fine/how-do-i-show-proof-of-insurance | 2/19/26: (Reg) Proof of Insurance: Should proof of insurance allow full payment or not? Currently we are allowing payment even with the work notes messaging. Should it show up as an additional message the "Make Payment" option is shown or should it be separate message and disallow payment. 2/23/26- MJB, It needs to come before make payment button as it's telling someone they may require proof of insurance, then have charge dismissed. | Dev Done | Should proof of insurance allow full payment or not? Meaning, should it show up additional message when for case's "Make Payment" option is shown or should it be separate message that disallow payment. Conditionally show proof of insurance
83 | IWR Messaging - Payment in lieu of appearance – Case/Citation (payable traffic) When “cases” > "caseIsEligibleForPayment": true, “baseCaseType”: “Traffic” | Medium | Testing | Search Results page | IWR Messaging | Sonant | “Fine” includes the fine amount established by the Court, and all related fees and surcharges required by law. 1. Unless you have already plead guilty, paying a fine on an offense(s) that does not require a court appearance constitutes a plea of guilty to the offense charged, will result in a conviction, and is an admission of the voluntary waiver of the following rights: a. Your right to a trial; b. To be represented by counsel (if a misdemeanor offense); c. To be presumed innocent until proven guilty beyond a reasonable doubt; d. To confront and cross-examine all prosecution witnesses; and e. To either remain silent or to testify for the defense. [Minn.R.Crim.P.23.03] 2. Failure to appear on a petty misdemeanor can also result in a conviction. Convictions for violating provisions of any law or ordinance regulating the operation of vehicles are reported to the Department of Public Safety and may be certified to your driving record. [Minn. Stat. § 171.01, subd. 29; § 609.02, subd. 5; § 169.95] 3. If no other offense on this case or citation requires a mandatory court appearance, and you can provide proof of insurance, do not pay this citation at this time. Contact the court payment center for instructions and information for paying other offenses on the citation. 4. If a citation includes more than one offense, then: a. If all of the offenses are payable (do not require a mandatory appearance), the total amount of the fines for all of the offenses must be paid. b. If you wish to enter a not guilty plea to one or more of the offenses, a court appearance is necessary. Do not pay at this time. |  | Dev Done | Use existing Header: Make Payment Did not remove these lines at start. Not sure if it was omitted by mistake. remove red "if paying online" - done "Currently Masterard and Visa…" "You may either pay the full amount…...." Remove existing para 3 for proof of insurance.. Otherwise, message is same as before. No messaging provided for non-traffic cases? So this will display for all cases..
84 | IWR Messaging - Make Payment – Case/Citation | Medium | Needs Discussion | Search Results page | IWR Messaging | Sonant | Header: MasterCard, Visa, and Discover are accepted. You may either pay the full amount of {…} or a different amount, plus a convenience fee of {ConvenienceFee} if paying online. Make a Payment of $ […] ({MinimumCasePayment}) Please note: Upon clicking Make Payment you are leaving the Minnesota Judicial Branch website. | Working on discusson of this requirement to commicate how these items are different. 3/11/26 | Need Input ?? | Is this duplicate and incomplete/partial version of #83 which is for traffic payments.. What should be displayed for non-traffic cases? MJB- Requirements are not duplicates, 83 and 84 are separate requirements. 3/11/26
85 | IWR Messaging - Payment Plan Payment – payments are current When “paymentPlan”: “planStatus”: “Early” or “On Time” | Medium | Testing | Search Results page | IWR Messaging | Sonant | This case is covered by a payment plan. One payment plan can cover multiple cases. Case Numbers covered by plan: Citation Numbers covered by plan: Your next installment amount is {…}. You can pay this installment amount plus a convenience fee of {ConvenienceFee}. You can pay a different amount up to the remaining balance of {…} plus the convenience fee if paying online. MasterCard, Visa, and Discover are accepted. Make a Payment of $ […] ({MinimumInstallmentPayment} Minimum) |  | Dev Done | 72vb258 has aged out and payment is now past due |  | test085
86 | IWR Messaging - Payment Plan Payment – Alternate Total Amount. When “paymentPlan” AND When “alternateTotalAmountDue” is “True” | Medium | New | Search Results page | IWR Messaging | Sonant | This case is covered by a payment plan. One payment plan can cover multiple cases. Case Numbers covered by plan: Citation Numbers covered by plan: We are unable to retrieve the details of your payment plan. You can make a payment of any amount up to the remaining balance of {…} plus the {ConvenienceFee}. MasterCard, Visa and Discover are accepted. Make a Payment of $ […] ({MinimumInstallmentPayment} Minimum) |  | Dev Done | Additional work
87 | IWR Messaging - Payment Plan Payment – payments are NOT current When “paymentPlan”: “planStatus”: “Late” | Medium | Testing | Search Results page | IWR Messaging | Sonant | This case is covered by a payment plan. One payment plan can cover multiple cases. Case Numbers covered by plan: Citation Numbers covered by plan: Because the installment due on {…} was not paid in a timely manner, this payment plan is now past due. You must pay the past due amount to avoid further collection action. MasterCard, Visa, and Discover are accepted. Make a Payment of $[…] ({MinimumInstallmentPayment} Minimum) |  | Dev Done | Additional work
88 | Display the following case information for criminal cases, even when no balance is owed on the case/citation: When Criminal (CR) - Both Adult and Juvenile criminal | High | Testing | Case Detail page | IWR Requirements 11 | Sonant | Display the following: - Case number - Citation number (when appicable) - Case type - Case location - Case status - Date filed - Offense information: offense count, charge description, and offense date, - Ticket date (when applicable) |  | Dev Done | Will show Citation Number, Offense information, Ticket data if available. |  | rtm104
89 | Display the following case information for non-criminal cases, even when no balance is owed on the case/citation: When Non-criminal - Civil (CV), Family (FA), Probate/MH (PR) | High | Testing | Case Detail page | IWR Requirements 12 | Sonant | Display the following: - Case number - Case type - Case location - Case status - Date filed |  | Dev Done | Non criminal cases will not show citation number, offense information and ticket date. |  | rtm104
90 | Display the following case-level party information, even when no balance is owed on the case: | High | Testing | Case Detail page | IWR Requirements 13 | Sonant | Display the following: - Connection type status when inactive (i.e., "Inactive") - Party connection type - Total balance owed ($) by entity - Active (scheduled; not stopped) payment plan information by entity (when applicable), to include: total remaining amount due on payment plan (if different from total balance owed), next installment amount due and when (due date), past due amounts. | There may have a few cases with alternate total balance due/due date where we cannot display next installment. | Dev Done | For case, display party Connection Type and Status For Case, display payor.TotalAmountDue. For PaymentPlan display Party Name, Total Amount Due, Current Amount, Next Amount Due/Date( if available ). If alternate amount is due, the API should pass null values for Next Amount Due/Date. |  | rtm105
91 | Display the case-level party's name (last, first) even when no balance is owed on the case | High | Testing | Case Detail page | IWR Requirements 14 | Sonant | Display except when: - Case-level party's base connection type is Victim (VI), Witness (WI), Ward (WA), or Other 2 (O2) - Case-level party's record has been marked as "Restricted from Public View" in MNCIS - Inactive party connection, removed/inactivated with reason "Party Connection Added in Error": |  | Dev Done | Sonant currently doesn't handle rule buisness rules for changing payor's name. The only business rule applied for party name is changing "Name not Available" to "Name not Displayed". If court doesn't want specific rules for not displaying party's name, the court can pass a empty string and then we consider UI change to handle it specially. Dev work for displaying name is done. |  | rtm105
92 | Display "Name Not Available" in place of the case-level party's name: | High | Testing | Case Detail page | IWR Requirements 15 | Sonant | Display when: - Case-level party's base connection type is Victim (VI), Witness (WI), Ward (WA), or Other 2 (O2) - Case-level party's record has been marked as "Restricted from Public View" in MNCIS - Inactive party connection, removed/inactivated with reason "Party Connection Added in Error" |  | Dev Done | 1. Assume MIS will return name not available in these cases. Sonant currently doesn't handle buisness rules for changing payor's name. Also assume if MIS returns as expected that we will make it an alias and display Name Not displayed per #98? 2. Sonant will change "Name Not Available" will be changed to "Name Not Displayed" Example case: 70-CV-25-48 |  | rtm105
93 | Display the following participant information only when a participant owes a balance on the case: | High | New | Case Detail page | IWR Requirements 16 | Sonant | Display the following: - Connection type status when inactive (i.e., "Inactive") - Participant connection type - Total balance owed ($) by entity - Active (scheduled; not stopped) payment plan information by entity (when applicable), to include: total remaining amount due on payment plan (if different from total balance owed), next installment amount due and when (due date), past due amounts. |  | Duplicate | Is this duplicate of #90? #90 ius when no balance and #93 is when balance owned.. Both have the same things for display in Work Note.The net effect is always show these fields. Mark it as duplicate. |  | rtm105
94 | Display the participant's name (last, first) when the participant owes a balance on the case | High | New | Case Detail page | IWR Requirements 17 | Sonant | Display except when: 'Public Case – Prior Volume' (PUBLIC) and no security assigned (no security assigned) (no security assigned) or one of the following case types: 'CHP', 'CHU', 'CHE', 'CNVCMI', 'CHM', 'CHR', 'CHT', 'VLP', 'CHV', 'DMA', 'CNVDAF', 'CNVDAG', 'CNVDAM', 'CNVDAT', 'HAR', 'OUT' - Participant's base connection type is Victim (VI), Witness (WI), Ward (WA), or Other 2 (O2) - Participant's record has been marked as "Restricted from Public View" in MNCIS - Inactive party connection, removed/inactivated with reason "Party Connection Added in Error" |  | Duplicate | Is this duplicate of #91? #91 is when no balance and #94 is when balance owed.. Both have the same things for display in Work Note. The net effect is always show the participant name. Marking it as duplicate. |  | rtm105
95 | Display "Name Not Displayed" in place of the "Name not Available." | High | Testing | Case Detail page | IWR Requirements 18 | Sonant | Display when: 'Public Case – Prior Volume' (PUBLIC) and no security assigned (no security assigned) or one of the following case types: 'CHP', 'CHU', 'CHE', 'CNVCMI', 'CHM', 'CHR', 'CHT', 'VLP', 'CHV', 'DMA', 'CNVDAF', 'CNVDAG', 'CNVDAM', 'CNVDAT', 'HAR', 'OUT' - Participant's base connection type is Victim (VI), Witness (WI), Ward (WA), or Other 2 (O2) - Participant's record has been marked as "Restricted from Public View" in MNCIS - Inactive party connection, removed/inactivated with reason "Party Connection Added in Error" | 2/19/26: (Reg) Display “Name not Available” under work notes conditions. This should be completed; We Assume MIS will return name not available in these cases. Sonant currently doesn't handle business rules for changing payor's name. Also assume if MIS returns as expected that we will make it an alias and display Name Not displayed per #98? 2. Sonant will change "Name Not Available" to "Name Not Displayed". Can we get sample case or cases to use for validation? R18 no sample cases in doc. 2/3/26 - Edited the description for requirement, which is currently in work after conversation with Sonant. Ready for testing. | Dev Done | 1.assume MIS will return name not available in these cases. Need sample case or citation. Also assume if MIS returns as expected that we will make it an alias and display Name Not displayed per #98? 2. Sonant will change "Name Not Available" will be changed to "Name Not Displayed" Can we get a case number to validate this data. One that returns Name Not Available Add case into MJB Notes
96 | When a party/participant has more than one connection to the case and a balance is owed, the party/participant name (or Name Not Available Online) should display only once; whereas, the connection type(s) displayed should be prioritized as follows: | High | Testing | Case Detail page | IWR Requirements 19 | Sonant | Priority: 1. Active Party > Inactive Party 2. Active Party > Inactive Participant 3. Active Party > Active Participant 4. Active Participant > Inactive Party 5. Active Participant > Inactive Participant 6. Multiple Active Parties = display all 7. Multiple Active Participants = display all 8. Multiple Inactive Parties = display all (except those removed with reason "Party Connection Added in Error") 9. Multiple Inactive Participants = display all (except those removed with reason "Party Connection Added in Error") | 2/29/26: (Reg) When a party/participant has more than one connection to the case and a balance is owed, the party/participant name (or Name Not Available Online) should display only once; whereas the connection type(s) displayed should be prioritized as follows: We implemented using the following rules. Please confirm if this is what is expected. Here's how the data is displayed: Single connection: "Defendant" Multiple Active Parties: "Defendant / Co-Defendant" Mixed priorities (Active Party + Inactive Participant): "Defendant" (only shows Active Party) Multiple Active Participants: "Witness / Victim" No connections: "-" | Dev Done | Assumption: Only party (partyId) would be returned that will have list of connection types. Implemented but not sure if this is what court wants.. Here's how it's displayed.. Single connection: "Defendant" Multiple Active Parties: "Defendant / Co-Defendant" Mixed priorities (Active Party + Inactive Participant): "Defendant" (only shows Active Party) Multiple Active Participants: "Witness / Victim" No connections: "-". Changed implementation to just return concanted list of connections, as MIS already provides the ordered list.
97 | Create "Case Selection Page" and have following fields appear | High | Testing | All Pages | IWR Requirement 9 | Sonant | Display: • Case Number • Citation Number • File Location • Casee Type • Charges If a particular field does not have data (for example if a case does not have a corresponding citation number), we would like to have a “-“ appear for the value |  | Dev Done |  |  | rtm106
98 | Display "Name Not Displayed" when results from MIS show "Name Not Available. | Medium | Testing | Search Results page |  | Sonant |  |  | Dev Done |  |  | test098 25jv253
99 | Remove help bubbles by radio buttons and have "help text" display in gray box above buttons. | Low | Testing | All Search Pages |  | Sonant | Case Number: Select one of the following search options. For information on how to find your case or citation number, review the [Citation and Case Number page.] | Have text inside brackets be a hyperlink to this page: https://mncourts.gov/pay-a-fine/citation-and-case-number | Dev Done |  |  | test099
100 | aXe tool flagging automation issue that aria-disabled user incorrectly. | Medium | Testing |  | QA Testing | Sonant | Expected Results: Ensure aria-disabled has correct value. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65988/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button Click/Enter View More Click Add to Cart Launch aXe tool and run scan Issue found when button are in disabled state | Dev Done | Changed aria-disabled to "false" or "true" on "Review Payment" button
101 | MN Judicial Branch logo doesn't have correct ALT text. Current ALT text says only "Logo" | Medium | New |  | QA Testing | Sonant | Expected Results: Logo must have proper ALT text. Azure bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65963/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button Inspect Logo on top left corner and see current ALT text | HPS |  |  | test101
102 | Screen reader tool getting search results announcement after a significant time while system is searching the data. Hence, screen reader user may not be able to understand either their search functionality working or not, they attempt to click "Find" button many times. | Medium | Testing |  | QA Testing | Sonant | Expected Results: If searching need more time than that must be alerts to the screen reader user like "Loading,,,,," or "Searching,,,,," etc. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65720/ | Launch testing page using chrome - https://qa3customer.sonant.com/MNPaymentApplication/ Enter random data into the "Case Number" input field Press/Enter "Find" button Listen for NVDA announcement | Dev Done | Two things will happen when Find is clicked.. 1. Set text on the form, so the screen readers will anounce "Searching for cases. Please wait…" 2. The Find button will be disable to prevent accidental double clicks. If no cases are found, the page will revert to original state ( thus enabling Find button ).
103 | axe found form controls doesn't have accessible name. | Medium | Testing |  | QA Testing | Sonant | Expected Results: All visual label must be associated with their input control. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65703/ | Launch testing page using chrome - https://qa3customer.sonant.com/MNPaymentApplication/ Launch browser DevTool Run axe tool Verify and analyze automation issue Wor | Dev Done | Duplicate of #117? Audited the entire application to sure all labels are associated with their input fields ( radio buttons, drop-down, text boxes ).
104 | Shopping cart link do not provide visual focus outline while focus stay on the link. currently only icon text color getting little bit change which is not sufficient for keyboard and low vision users. | Medium | Testing |  | QA Testing | Sonant | Expected Results: All keyboard navigable element has visual focus outline that are clearly visible. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65989/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button Click/Enter View More Click Add to Cart Use TAB key to navigate all mouse clickable element | Dev Done | Add dotted box around focussed elements..
105 | Visual text for button element do not have enough contrast. | Medium | Work in progress |  | QA Testing | Sonant | Expected Results: All textual information must have enough contrast radio. Minimum contrast should be 4.5:1 for regular text size. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65964/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button See color contrast for the "Complete" button | HPS
106 | Hover able elements on CVV field (e.g., CVV position) is not available to the keyboard only user nor have screen reader instruction where and how to find CVV# | Medium | Work in progress |  | QA Testing | Sonant | Expected Results: CVV card information must be available and accessible to keyboard user or at least same information should be provided to the screen reader. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65979/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button Use keyboard to navigate interactive elements Verify if all mouse clickable and hover able elements are available to keyboard user | HPS
107 | Page requires two dimensional scrolling while zoomed at 400% which causing difficulties for small devices users to see and navigate the content. Text are overlaps and not clearly visible while zoomed at 400% | Medium | Work in progress |  | QA Testing | Sonant | Expected Results: Ensure page content doesn't requires two dimensional scrolling. Ensure all text are clearly visible and read able without overlaps, cuts off Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65977/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button Zoom the page at 400% | HPS
108 | While page zoomed at 200% text gets overlaps and are not readable. | Medium | Work in progress |  | QA Testing | Sonant | Expected Results: All text and information must be readable without cuts off or overlaps. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65967/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button Zoom the page at 200% | HPS
109 | Error suggestion are not associated with their input field. | Medium | Work in progress |  | QA Testing | Sonant | Expected Results: All error suggestion must be associated with the input fields. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65966/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button Click "Complete" button without entering requires data | HPS
110 | Link text do not have visual cues to understand that they are clickable elements. Color blind user will not be able to understand which text is link text. | Medium | Work in progress |  | QA Testing | Sonant | Expected Results: UI elements including link must not rely on color only beside color they must have visual cues to understand they are clickable elements. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65965/ | Open testing application - https://qa3customer.sonant.com/mnpaymentapplication Enter Citation or Case Number Click Pay now button Links without visual cues | HPS
111 | Color contrast is not sufficient on the breadcrumb text while focus landed on the elements. Current color contrast is 1.6 or similar. | Medium | Testing |  | QA Testing | Sonant | Expected Results: Ensure all text regardless their state must have enough color contrast so all users will be able to see them clearly. minimum contrast ratio is 4.5:1 Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65937/ | Open testing page using chrome - https://qa3customer.sonant.com/MNPaymentApplication/Case/CaseDetail?caseId=1629848450&payorId=1618201187 Select Driver License radio button and enter data Launch color contrast analyzer tool and verify foreground and background color | Dev Done |  |  | test111
112 | Link text is not clear and provide full meaning/purpose of the link. | Medium | Testing |  | QA Testing | MJB Team | Expected Results: Link text should provide more clear information about it's purpose. Bug: 65779 https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65779/ | Open testing page using chrome - https://qa3customer.sonant.com/MNPaymentApplication/Case/CaseDetail?caseId=1629848450&payorId=1618201187 Launch NVDA Enter Case Number (e.g. 19-AV-VB-22-4325) Enter Find button Tab onto "Click to view" link and listen for NVDA announcementLaunch color contrast analyzer tool and verify foreground and background color | Dev Done | Not sure what the issue is Based on other requirements, made the full iine "You may have other payable cases or citations. Click to view" a hyperlink, so not sure if it's still an issue.
113 | Axe automation tool found there is at least one element used inappropriate aria property. | Medium | Testing |  | QA Testing | Sonant | Expected Results: Verify axe tool is not flagging any issues. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65794/ | Open testing page using chrome - https://qa3customer.sonant.com/MNPaymentApplication/Case/CaseSelection Enter case number and go to next Click "Click to view" link on case details page Launch axe tool Run for automation and see issue related to invalid aria used | Dev Done | Is it duplicated of #100? Couldn't find any more axe violations after #100 was fixed.. If there are any other issues, need specific ways to reproduce the violation.
114 | Visual label and accessible name is not matching. hence voice prompt tool will not be able to recognized the commands. | Medium | Testing |  | QA Testing | Sonant | Expected Results: Visual label and accessible name must be same or at least accessible name start with visual label. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65781/ | Open testing page using chrome - https://qa3customer.sonant.com/MNPaymentApplication/Case/CaseDetail?caseId=1629848450&payorId=1618201187 Launch NVDA Enter Case Number (e.g. 19-AV-VB-22-4325) Enter Find button Navigate to the "Search Again" button and listen for NVDA | Dev Done | Made all accessible name same as visible name, for all the buttons.
115 | Visually bolder text doesn't have semantics markup. | Medium | Testing |  | QA Testing | Sonant | Expected Results: All text must have proper and semantics mark up the way they are presented on screen. https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65774/ | Open testing page using chrome - https://qa3customer.sonant.com/MNPaymentApplication/Case/CaseDetail?caseId=1629848450&payorId=1618201187 Enter Case Number (e.g. 19-AV-VB-22-4325) Enter Find button Inspect bolder text and see their tag type | Dev Done | Found three instances where bold tags were used..<b>a not guilty plea</b>.. Changed from visual <b> to sematic markup <strong>. Other two occurenaces.. <b>Please Note:</b>
116 | Heading order is not logical and intuitive. hence, understanding the relationship is confusion. | Medium | Testing |  | QA Testing | Sonant | Expected Results: First heading on the page should be found as H1 tag than all other heading must follow the logical heading order H2, H3, H4 Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65772/ | Open testing page using chrome - https://qa3customer.sonant.com/MNPaymentApplication/Case/CaseDetail?caseId=1629848450&payorId=1618201187 Enter Case Number (e.g. 19-AV-VB-22-4325) Enter Find button Launch ANDI and verify heading order | Dev Done | Removed h2 element in header which was breaking hierarchy.
117 | State label is not associated with the combobox Date field cues MM/DD/YYYY implemented as placeholder. hence, it gets disappear while user start typing therefore it will be difficult for cognitive user to understand the format. | Medium | Testing |  | QA Testing | Sonant | Expected Results: All label and cues must be associate with their. State visual label must be associate with combobox Date format should be displays at all time for cognitive users. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65761/ | Open testing page using chrome - https://qa3customer.sonant.com/mnpaymentapplication Turn on NVDA Navigate using keyboard Listen for the field label and cues | Dev Done | In date of birth, the mask "mm/dd/yyyy" will always be visible to guide users. Audited the entire application to make sure all labels are associated with their input fields ( radio buttons, drop-down, text boxes ).
118 | Upon keyboard focus land on date field, date calendar open. however, user with keyboard only are not able to navigate calendar using keyboard. | Medium | Testing |  | QA Testing | Sonant | Expected Results: Calendar must be accessible and operable using keyboard alone with all other features within calendar components. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65750/ | Open testing page using chrome - https://qa3customer.sonant.com/mnpaymentapplication Turn on NVDA Navigate using keyboard See page while focus onto date field | Dev Done | Using Html calendar with support full ADA/ARIA.
119 | Driver's License Number, DOB are requires field. however, they do not have visual indication to understand which fields are required. | Medium | Testing |  | QA Testing | Sonant | Expected Results: All required input fields must have visual indication to understand the fields are required. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65729/ | Open testing page using chrome - https://qa3customer.sonant.com/mnpaymentapplication Turn on NVDA Navigate the radio button using keyboard Select DL radio button Visually review requires fields do not have visual cues | Dev Done | Added visual indicator * in red color.. Uses both color (red) and symbol (asterisk) for accessibility
120 | User with screen reader are not able to navigate all radio buttons using arrow keys. When users press right or down arrow from first radio button focus immediately jump to the input field and not allowing to navigate the third option. | Medium | Testing |  | QA Testing | Sonant | Expected Results: Focus must not shift immediately upon UI (radio button) received keyboard focus. User must be able to select 3rd radio button by pressing down/right arrow after 2nd radio button. Azure Bug: https://j00pcourttfs.courts.state.mn.us/tfs/DSSProjects/Statewide%20Payment%20System/_workitems/edit/65722/ | Open testing page using chrome - https://qa3customer.sonant.com/mnpaymentapplication Turn on NVDA Navigate the radio button using keyboard Press arrow keys to navigate between radio button Observed if you can navigate all radio buttons | Dev Done | Allow key navigation between radio button.. After selecting radion button, tab to focus on first field to enter.. Pressing enter will also work but trigger field validation
121 | Skipping payment summary page when checking out from case detail page – confirm must show payment summary page. | High | Work in progress | Payment Summary page | Testing | Sonant |  | o Sonant’s suggestions: - Will add convenience fee amount towards bottom of page near may payment amount area - Add total amount into “Pay Now” button (Pay Now $17.34) • The customer’s ability to manipulate cart and breadcrumbs are barriers for Sonant to make the experience consistent o Sonant will send a mockup so MJB can run past legal. We’ll run past QA for ADA/WCAG. 3/9/26 3.16.26 Ensure text in button is digitally accessible | In QA | Single item behavior is to directly to go HPS to make the payment without going thru the payment summary page. ( to facilitate quick checkout and similar behavior to current prod ). Payment summary page will only show in Multi item cart mode. To show payment summary for single cart will be quite a refactor, as it wasn't designed for single cart checkout. With remove buttons, and additional consideration for breadcrumbs and back button, there will be changes to the flow that need to be considered and will take time. One option would be to show the Conveniece fee at the bottom, so the user know how much they are paying and also have the button text updated to say what amount they will be paying. Say if they entered $20 for the payment amount, the button text can be made to read "Pay Now $22.34". This only applies to single item cart mode. In multi cart mode, the button will continue to be "Add to Cart" Updated: Added text "Please Note: A convenience fee of $2.34 will be added to this amount." at bottom near the payment amount input.. Also updated the button to dynamically show the total amount including the convenience fee. This works for both single payment case or payment plan. To test 70-VB-25-77 (PP), 70-VB-25-38 (case)
122 | Not removing cases that do not require payment from case selection page (citation search of 1). | Medium | MJB Input Needed | Party Selection page | Testing | Sonant | This was discussed with Sonant during out 1/12 call (Mary OOO), and reiterated during our 1/26 call. | MJB was still expecting a result for 1:1 search results based off what person entered – people will lookup a case/citation. o MJB requirements were for case/citation search to return results if match is found. For bulk searches, we’re not showing $0 cases/cases that have no action. o Or MJB needs to change language about not finding a case/citation that matches. 3/9/26 | In QA | Agreed. It was discussed but not written down. Removing zero due cases from the case selection page. Now when you search for Citation Number 1, there are no cases with due amount and so it shows a empty case selection page. In this scenario, if there are no cases with amount due should we tell the user there are no cases found and redirect back to search page (ie just remain on the search page and show "case not found. ) 3/9 - Discussed with court. Will filter cases with no amount due if case number or citation number search yields multiple case results. For searches that yield single case, will always show the case information.
123 | As for payment eligible cases, it seems like there may be mixed behavior based on whether the person truly has additional cases | Medium | MJB Input Needed | Related Payable Cases page | Testing | Sonant |  | For example, if I search for case 10-FA-26-1, select “Party, Test” on the party selection page, then opt-in to the subsequent search, I am only presented the cases in which there is a balance due for that party (which does not include the original case searched). However, if I search for case 04-CO-20-149 and select the party without a balance (not the business one), then opt-in to the subsequent search, I receive the original case with the zero balance in the subsequent search. This party does only have this one case in the system. Could this be an attempt to retain the customer’s initial search information there is only the one case found, rather than presenting them with a no cases found message or something like that? | In QA | To answer the question.. Any new search clear all previous search results and so doesn't retain any information from previous results. Does the court want to not show any related cases or payment plans if the payor doesn't owe for the related cases retrieved? ( similar to case selection page ).. Need confirmation 3/9 - Discussed with court to filter out cases/payment plan with no amount due for secondary search results.
124 | “Back to Top” button behavior – this button doesn’t display until you scroll down the page a little bit. Is this intentional or should it appear as soon as the user begins scrolling? | Medium | MJB Input Needed |  | Testing | Sonant |  | Ideally, we don’t want the user to be ½ way down the page before it displays. Adjust to height of header/banner. | In QA | This is intentional.. The button shows up only when the page scrolls beyond a scroll threshold (300px) vertically. Similar to how it's implemented on MCRO site. Design guidelines used for these buttons.. Conditional Visibility: The button should be hidden by default and only appear after the user has scrolled a significant distance down the page (e.g., more than four screen lengths). This prevents interface clutter on short pages where scrolling back manually is not an effort. Fixed Position: Once visible, the button remains in a fixed, "sticky" position, typically the lower-right corner of the browser window. This placement is where users expect to find it and ensures it is always accessible without covering important content. 3/9 - Make the button show up when the page is scroll beyond the header height.
125 | There are multiple font types. Pick one san-serif font | Medium | Deploy/Launch | All Pages | Testing |  |  | Passed testing via Team 3/9/26, moved status to Deploy | Dev Done | Based on email from Mary Changed body font from "Open Sans, Helvetica, Arial, sans-serif;" to "system-ui, -apple-system, "Segoe UI", Roboto, "Helvetica Neue", Arial, sans-serif". Font size is set to 1rem ( appr 16px and varies with viewport ).
126 | Case Details – ticket date – should be “citation date”. Schema does state ticket, but site should state citation. | Medium | Deploy/Launch | Case Detail page | Testing | Sonant |  | Passed testing via Rebecca, moved status to Deploy 3/9/26 | Dev Done | Oops.. Found one place stil had "ticket" notation.. Changed it.
127 | Case not filtered out of search result | Medium | Deploy/Launch | Search Results page | Testing | Sonant | 70-CV-25-40 should not be listed and instead, filtered out from the results as wasSearchedOn = True AND payorIsEligibleForPayment = False. | Image attached to PDF sent to Reg and Dean on 3/3/26 Passed testing via Wally 3/9/26, moved status to Deploy | Dev Done | 1. Changed column "Due Amount" to "Amount Due" in Cases grid. 2. Filtered out payorIsEligibleForPayment=false rows for both Cases and PaymentPlans.
128 | Incorrect payment plan amount remaining shown. | Medium | Deploy/Launch | Payment Plan Details | Testing | Sonant | 70-VB-25-78; $200 is the current amount due (because it is the delinquent amount), not the ‘remaining’ balance | Image attached to PDF sent to Reg and Dean on 3/3/26 Passed testing via Leah 3/9/26, moved status to Deploy | Dev Done | 1. Changes text a) "Payment Plan Total" to "Total Amount Due" b) "Payment Plan Remaining" to "Current Amount Due" 2. Allow upto TotalDueAmount. Changed min/max validation to use the TotalDueAmount as max amount. 3. Also changed body text that says "to the remaining balance of" to use TotalDueAmount
129 | This payment plan is past due, so the past due message should be displayed. | Medium | Deploy/Launch | Payment Plan Details | Testing | Sonant | 70-VB-25-78; | Image attached to PDF sent to Reg and Dean on 3/3/26 Passed testing via Leah 3/9/26, moved status to Deploy | Dev Done | Fixed. This was a bug.. It was doing a doing a case sensitive check of paymentPlanStatus ( "Late" as "late" ).
130 | Incorrect data field labels. | Medium | Deploy/Launch | Case Detail page | Testing | Sonant | 70-VB-25-39; Correct: Citation Date, Incorrect: Ticket Date Correct: Total Amount Due, Incorrect: Total Owned | Image attached to PDF sent to Reg and Dean on 3/3/26 | Dev Done | Changed text.
131 | Inactive Defendant shown on page | Medium | MJB Input Needed | Case Detail page | Testing | Sonant | 70-CV-25-47, 43-CV-26-5 | 3.13.26 email to Raj that they team would like the following: • Bank (inactive); Topic (inactive) • Bank (inactive), Topic (inactive) Image attached to PDF sent to Reg and Dean on 3/3/26 | In QA | Not sure how to handle an Inactive defendant. #96 in the excel, seems to indicate to show all defendants irrespective of inactive state or participant. Are there any additional rules for handling defendants base on isActive or asParticipants flags? 3/9 - For inActive parties, show (inactive) near the connection like "Bank (inactive) / Topic (inactive)". Need confirmation from the court on the format. What to do if the connection's asParticipant is false?
132 | Related case for payment plan left "hidden" on results | Medium | MJB Input Needed | Search Results page | Testing | Sonant | When searching for 25-VB-25-18, then clicking “You may have other payable cases or citations. Click to view”, then: | Image attached to PDF sent to Reg and Dean on 3/3/26 | Need Input ?? | This payment plan has two cases 25-VB-25-18 and **Hidden**. There is no case number for the hidden case. What is expected in this scenario? ( see API data for this case ). "planCases": [ { "caseNumber": "25-VB-25-18", "id": 1629859386, "citationNumbers": [ "061720250952" ], "caseIsEligibleForPayment": true, "hasDLSuspension": false, "requiresMandatoryCourtAppearance": false, "requiresCourtContact": false, "unscheduledAmountDue": null }, { "caseNumber": "**Hidden**", "id": -1, "citationNumbers": [ "***Hidden***" ], "caseIsEligibleForPayment": false, "hasDLSuspension": false, "requiresMandatoryCourtAppearance": false, "requiresCourtContact": true, "unscheduledAmountDue": null } ]
133 | Label for "Citation Numbers covered by plan:" appears and does not need to be shown. | Medium | Deploy/Launch | Payment Plan Details | Testing | Sonant | 18-FA-25-6; This is a non-criminal case and therefore, will never have a citation number. Do we still want this label to appear? | Image attached to PDF sent to Reg and Dean on 3/3/26 Passed testing via Rebecca 3/9/26, moved status to Deploy | Dev Done | Not showing if there are no citation numbers to display.
134 | Message displaying incorrect information is displayed. | High | Deploy/Launch | Case Detail page | Testing | Sonant | 25-FA-25-15; This is a non-criminal case and therefore, there should be no license suspended message displayed | Image attached to PDF sent to Reg and Dean on 3/3/26 Passed testing via Wally 3/9/26, moved status to Deploy | Dev Done | Hiding "License Suspended" for non-criminal ( CaseCategory != "CR" ) cases.B57+B59
135 | Unable to make payment on payment eligible case | Medium | Deploy/Launch | Payment Plan Details | Testing | Sonant | There is an error and/or misunderstanding on payment plans where the “planStauts”: “Early”. Sonant may be using the currentAmountDue: 0 to determine whether a payment can be made. | • Unable to make payment on payment eligible case a. Steps to reproduce: i. Complete a case number search for 04-CR-22-672 or 04-CR-22-900 ii. Actual Result: Payment Plan Details reflect Payment Plan Total: $185.00, Payment Plan Remaining: $0.00, and Next Installment Due Amount: $185.00. Message: Unable to Make Payment This citation is not able to be paid using this system because there is no amount due on this citation. iii. Expected Result: Payment should be allowed as the response returns the data for an eligible payment. Passed testing via Leah 3/9/26, moved status to Deploy | Dev Done | This is related to #128, where all validations were done based on CurrentAmountDue.. Fixed to use TotalAmountDue as the total amount due remaining on the case and all validations would be based on it.
136 | There is a difference in the a user’s shopping cart results experience that appears to be related to whether there is any sort of balance on the case or not. After searching by case, making the desired party selection, and selecting the link to view possible additional cases: | Medium | New | Case Detail page | Testing | Sonant | Example case: 11-CV-22-102. If no balance exists for any party on the on the case, the user stays on the case details page and a message pops up at the top indicating no additional cases were found. If there is a balance on the case, the user is brought to the search results page with only that case listed and a zero amount due as the party selected is not the one with the balance owed. | We're getting a different result when searching 11-CV-22-33 (chose Colleen or John on subsequent screen)., then click on the “other payable cases” link. 3.16.26 mtg- Would like message closer to the button - Court will run past team to see if it's wanted in both places (top and bottom) | In QA | The issue with 11-CV-22-33 was there was atleast one payor who had an outstanding amount.. So when doing secondary search for payors with no outstanding due, the secondary search still returned the case based on other payor who had an outstanding amount. Made few changes when accessing secondary search.. 1. Current rule is, if secondary search returns no cases it will remain on case detail page. 2. Additional rule.. If secondary search return exactly 1 case which is the same as the current case being viewed ( in case detail page ), it will remain on case detail page. 3. Additional rule.. If secondary search yields multiple results ( cases or payment plans ) but the current viewing payor doesn't have any amount due on these, it will remain on case detail page.
137 | We would like the time removed from the message presented when a payment plan installment is past due and only have the date of the missed installment. | Medium | New | Payment Plan Details | Testing | Sonant | Example: 70-VB-25-78 | Drop time, not date. Keep date 3.16.26 mtg-Remove the time |  | Please provide case number and what needs to be removed with an example.
138 | A correction is needed to the value presented when making a payment. This amount appears to be pulling in the total amount due and should be presenting the current amount due. | Medium | New | Payment Plan Details | Testing | Sonant | Example: 70-VB-25-78 | Should display "Current Amount Due" in the payment field with a max of Total Amount Due. 3.16.26 mtg-Should default to the current amount due, not the total |  | Please provide case numbers and steps to reproduce the issue.
139 | The listing same citation number per offense count on the Case Details page | Medium | New | Case Detail page | Testing | Sonant | Example: 69DU-VB-21-5135. While MIS includes the citation number per count, Sonant should only be displaying distinct/unique values as yes it is possible for a different citation number to exist per count, but the occurrence is rare enough that we don’t want to repeat duplicate citation numbers for the sake of the few. |  | In QA
140 | On the opening screen’s Driver’s License Number search, the DL, State, and DOB field boxes are misaligned in both size and placement. | Low | New | All Search Pages | Testing | Sonant |  | 3.16.26 mtg- Sonant states they've corrected this | In QA
141 | If a user cancels on the HPS pages, they are brought back to the search/home page and an error is presented | Medium | MJB Input Needed | All Search Pages | Testing | Sonant | 3.13.26 Expected Result: Return to the case detail page or payment summary page if "Cancel" is pressed on payment page. Awaiting info on expected result | 3.16.26 mtg- Sonant states that going back to the pay now page or payment summary would be a challange. Sonat wants to know if MJB would load balance the appliccation and how critical this feature is this going forward? | Need Input ??
142 |  |  | New
143 |  |  | New
144 |  |  | New
145 |  |  | New
146 |  |  | New
147 |  |  | New
148 |  |  | New
149 |  |  | New
150 |  |  | New
151 |  |  | New
152 |  |  | New
153 |  |  | New
154 |  |  | New
155 |  |  | New
156 |  |  | New
157 |  |  | New
158 |  |  | New
159 |  |  | New
160 |  |  | New
161 |  |  | New
162 |  |  | New
163 |  |  | New
164 |  |  | New
165 |  |  | New
166 |  |  | New
167 |  |  | New
168 |  |  | New
169 |  |  | New
170 |  |  | New
171 |  |  | New
172 |  |  | New
173 |  |  | New
174 |  |  | New
175 |  |  | New
176 |  |  | New
177 |  |  | New
178 |  |  | New
179 |  |  | New
180 |  |  | New
181 |  |  | New
182 |  |  | New
183 |  |  | New
184 |  |  | New
185 |  |  | New
186 |  |  | New
187 |  |  | New
188 |  |  | New
189 |  |  | New
190 |  |  | New
191 |  |  | New
192 |  |  | New
193 |  |  | New
194 |  |  | New
195 |  |  | New
196 |  |  | New
197 |  |  | New
198 |  |  | New
199 |  |  | New
200 |  |  | New
201 |  |  | New
202 |  |  | New
203 |  |  | New
204 |  |  | New
205 |  |  | New
206 |  |  | New
207 |  |  | New
208 |  |  | New
209 |  |  | New
210 |  |  | New
211 |  |  | New
212 |  |  | New
213 |  |  | New
214 |  |  | New
215 |  |  | New
216 |  |  | New
217 |  |  | New
218 |  |  | New
219 |  |  | New
220 |  |  | New
221 |  |  | New
222 |  |  | New
223 |  |  | New
[7 empty] | Citation Number: Select one of the following search options. For information on how to find your case or citation number, review the [Citation and Case Number page.] | Have text inside brackets be a hyperlink to this page: https://mncourts.gov/pay-a-fine/citation-and-case-number | Dev Done
[7 empty] | Driver's License: Select one of the following search options. A driver’s license search may not include all of your cases or citations. If you have questions or need more information, please contact the MN Court Payment Center (CPC). |  | Dev Done

## API Items
Number | Description | Page | Status | Notes | Testing | More information Needed
1 | occasionally we get cases with a shopping cart key where there are no other cases | Related Payable Cases page | MIS Bug | see 19-AV-vb-15-1197 | got shopping cart key for other items but none there error handling is fine on the site but why are we getting the key?
2 | Enter badly formatted data in case search ie 23c123 | Search Page - Find Your Case | MIS Bug | Currently MIS has a bug that in many cases will return an api error. We are displaying the error: API Error: BadRequest - "Internal Error" API should be returning No cases found matching your search criteria. | failed API | What should the site do when the api returns errors?
3 | Enter badly formatted data in case search is "Enter words into the case seach" | Search Page - Find Your Case | MIS Bug | Currently MIS has a bug that in this case causes a timeout We are displaying the error: Request timeout. Please try again." How should we handle a timeout | failed API | What should the site do when the api returns errors / times out? 12/24 - MJB not able to replicate. "Renturns NO cases match your search"
4 | search by citation and enter 1 | Search Page - Find Your Citation | Sonant Bug | 1 returns many 0 dollar parties. When searching for 1 or 2 mis returns many 0 due cases that are closed. | failed API | This isn't an API failure, the number 1 is returning multiple citations. Sonant needs to determine which citation is being searched before they jump to the party selection page.
Searching for 3 returns a single non payable case 4 and above return correctly - no citation found
5 | search by case and enter 1 | Search Page - Find Your Case | Closed | returns API Error: BadRequest - "Internal Error" | failed API | 12/24 - MJB not seeing this, returns "No cases match your search."

## Ref List
Stakeholders
Rebecca Becker |  | QA Site
Amanda Bloodsaw | Low | Webservice examples
Leah Cairns | Medium | IWR Messaging Document
Rebecca Carter | Blocker
Dean Goddette | High
Liz Halet
Linda Herman
Mary Kenefick
Rick Konkoly-Thege
Adam McLemore
Andrey Safonov
Reg Rawdon | Open/Closed/Unknown
Dan Tamkin | Open
Wally Wallestad | Closed
Sonant | Unknown
Minnesota Judical Branch | Open/Text
Open/BizRule
All Pages
All Search Pages | State | State Definitions
Search Page - Find Your Case | New | Change has been newly added and needs to be reviewed.
Search Page - Find Your Citation | Needs Discussion | This item needs to be disucssed during a meeting.
Search Page - Find Your Citation by DLN | Draft | The to-do solution details are still being drafted.
Party Selection page | New | Change has been newly added and needs to be reviewed.
Case Detail page | Scoping | The to-do solution is being triaged and the scope of the defect and its fix is being analyzed.
Related Payable Cases page | MJB Input Needed | More information is needed from MJB to proceed.
Search Results page | Work in progress | Sonant is working on the solution for the to-do item.
Payment Summary page | Testing | Sonant is testing the to-do solution based on the scope provided.
All HPS Pages | Deploy/Launch | Sonant is ready to launch the solution for the to-do item.
HPS1 | Closed Complete | The solution for the to-do item is deployed into the product.
HPS2 | On Hold | The solution for the to-do item is put on hold due to any blockers and until further review.
HPS3 | Cancelled | The MJB and Sonant teams cancel working on this to-do item.
HPS4
Payment Receipt page
Payment Plan Details
| State | Definition
| Pass | Passed the QA test
| Fail | Failed the QA test
| n/a | Not applicable, canceled or otherwise not relevant